## Sprint Planning
Project Name | ShoeMart
Scrum Team | Dev, QA, PO, Scrum Master etc.
Created By | Product Owner
Epic | User Story ID | Feature/Title | User Story | Story Points | Sprint
For a new e-commerce portal to launch(sportshoes.com), the highest business value will be when a new user is able to buy an item from the website. | US001 | First time visitor can make the payment as a guest user without having to register | As a first-time visitor to the e-commerce website, I want to be able to buy a listed product, So that I can se the product I buy. | 8 | 1
| US002 | New user can register on the website | As a first-time visitor to the e-commerce website, I want to be able to register on the website, So that I can browse and buy listed products from the website. | 3 | 1
| US003 | Registered User can Browse items listed | As a Registered Website User, I want to be able to browse listed products from the website. So that I can make my choice and buy a listed product from the website. | 5 | 2
| US004 | Registered User can add items to the cart | As a Registered Website User, I want to be able to add items to the cart. So that I can buy a listed product from the website. | 5 | 3
| US005 | Registered User can make payment for the items added to the cart. | Registered User can make payment for the items added to the cart. | 8 | 4
| US006 | Administration login | Required to access admin page and to manage the website.He should able to change his password | 7 | 5
| US007 | admin to Browse the list of users Managing the products | Admin should able to manage the products in the store including categorizing them and Amin should able to browse the list of users who have signed up and be able to search users | 6 | 6
| US008 | Admin to see Purchase reports | Admin should able to see purchase reports filtered by date and category | 6 | 6

## Product Catalog
Project Name | ShoeMart
StakeHolders/Customers/Users | abc/xyz/zxc etc.
Created By | Product Owner
Epic | User Story ID | Feature/Title | User Story | Status | Acceptance Criteria
For a new e-commerce portal to launch(sportshoes.com), the highest business value will be when a new user is able to buy an item from the website. | US001 | First time visitor can make the payment as a guest user without having to register | As a first-time visitor to the e-commerce website, I want to be able to buy a listed product, So that I can se the product I buy. | New
| US002 | New user can register on the website | As a first-time visitor to the e-commerce website, I want to be able to register on the website, So that I can browse and buy listed products from the website. | New
| US003 | Registered User can Browse items listed | As a Registered Website User, I want to be able to browse listed products from the website. So that I can make my choice and buy a listed product from the website. | New
| US004 | Registered User can add items to the cart | As a Registered Website User, I want to be able to add items to the cart. So that I can buy a listed product from the website. | New
| US005 | Registered User can make payment for the items added to the cart. | Registered User can make payment for the items added to the cart. | New
| US006 | Administration login | Required to access admin page and to manage the website.He should able to change his password | New
| US007 | Managing the products and Browse the list of users | Admin should able to manage the products in the store including categorizing them and able to browse the list of users who have signed up | New
| US008 | Purchase reports | Admin should able to see purchase reports filtered by date and category | New